Project Management and Scheduling 27/01

- Demeulemeester-Herroelen: calculate resource based and critical sequence based lower bound for the minimal delaying alternatives, you had three different resources. I had minimal delaying alternative 2<.3 with a CSLB of 13 and 2<.1 with a CSLB of 11 (I had same delaying alternatives but 13 as CSLB for both)

- Labeling algorithm: in a table, AoA-network was given. You had to draw the AoA-network, give the critical path length (7?) and then crash the project length 2 time units. you also had to give the cost of crashing the activities and the optimal durations in the end (I had a total cost of 8) (x2)

- Starting time criticality heuristic: flow chart and table were given, only had to add unavoidable resource arcs and then solve the algorithm

- Theory questions:

  - Which precedence constraints are absolutely necessary (LP layout with on/off step variables)

  - How many minimal forbidden sets are present in this network (I had 14?) (x2)

  - One point cross-over (mother/father => daughter)

  - 12 - 24 I 13 → calculate expected cost of this policy (p’s and Wi’s, Wb and Wr were given, I had 23,12 or something) (x2)

  - calculate FS’ when SS, SF, FF and durations of two activities are given (was this 2?) (x2)