## Slide 1: Solutions Homework 1

## Slide 2: Exercise 1: AoN representation
a
c
b
d
h
e
f
g
j
i
17
3
20
11
2
12
7
2
10
6

## Slide 3: AoN: Time analysis
Act. | ES | EF | LS | LF | TS | FS | SS | IS
A | 0 | 17 | 6 | 23 | 6 | 0 | 6 | 0
B | 0 | 3 | 5 | 8 | 5 | 0 | 5 | 0
C | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0
D | 3 | 14 | 9 | 20 | 6 | 3 | 1 | -2
E | 3 | 5 | 18 | 20 | 15 | 12 | 10 | 7
F | 3 | 15 | 8 | 20 | 5 | 5 | 0 | 0
G | 17 | 24 | 23 | 30 | 6 | 6 | 0 | 0
H | 20 | 22 | 28 | 30 | 8 | 8 | 8 | 8
I | 20 | 30 | 20 | 30 | 0 | 0 | 0 | 0
J | 20 | 26 | 24 | 30 | 4 | 4 | 4 | 4
  ISi = min {ESTj | j ϵ Si} – max {LFTj | j ϵ Pi} – di

## Slide 4: AoA representation 1
7
1
2
3
4
8
5
B:3
E:2
C:20
9
6
G:7
A:17
D:11
H:2
F:12
I:10
J:6

## Slide 5: AoA 1: Time analysis
Act. | ES | EF | LS | LF | TS | FS | SS | IS
A | 0 | 17 | 6 | 23 | 6 | 0 | 6 | 0
B | 0 | 3 | 5 | 8 | 5 | 0 | 5 | 0
C | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0
D | 3 | 14 | 9 | 20 | 6 | 0 | 1 | -5
E | 3 | 5 | 18 | 20 | 15 | 0 | 10 | -5
F | 3 | 15 | 8 | 20 | 5 | 5 | 0 | 0
G | 17 | 24 | 23 | 30 | 6 | 6 | 0 | 0
H | 20 | 22 | 28 | 30 | 8 | 8 | 0 | 0
I | 20 | 30 | 20 | 30 | 0 | 0 | 0 | 0
J | 20 | 26 | 24 | 30 | 4 | 4 | 4 | 4
Event | Early occurrence | Late occurrence | Event slack
1 | 0 | 0 | 0
2 | 3 | 8 | 5
3 | 5 | 20 | 15
4 | 14 | 20 | 6
5 | 20 | 20 | 0
6 | 17 | 23 | 6
7 | 20 | 20 | 0
8 | 20 | 28 | 8
9 | 30 | 30 | 0
  TSij = tj(L) – ti(E) – yij = tj(L) – EFTij = LFTij - EFTij
  FSij = tj(E) – ti(E) – yij = tj(E) – EFTij
  SSij = tj(L) – ti(L) – yij = LSTij – ti(L)
  ISij = tj(E) – ti(L) – yij

## Slide 6: AoA representation 2
7
1
2
3
4
8
5
B:3
E:2
C:20
11
6
G:7
A:17
D:11
H:2
F:12
I:10
J:6
9
10

## Slide 7: AoA 2: Time analysis
Act. | ES | EF | LS | LF | TS | FS | SS | IS
A | 0 | 17 | 6 | 23 | 6 | 0 | 6 | 0
B | 0 | 3 | 5 | 8 | 5 | 0 | 5 | 0
C | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0
D | 3 | 14 | 9 | 20 | 6 | 0 | 1 | -5
E | 3 | 5 | 18 | 20 | 15 | 0 | 10 | -5
F | 3 | 15 | 8 | 20 | 5 | 0 | 0 | -5
G | 17 | 24 | 23 | 30 | 6 | 6 | 0 | 0
H | 20 | 22 | 28 | 30 | 8 | 8 | 0 | 0
I | 20 | 30 | 20 | 30 | 0 | 0 | 0 | 0
J | 20 | 26 | 24 | 30 | 4 | 4 | 0 | 0
Event | Early occurrence | Late occurrence | Event slack
1 | 0 | 0 | 0
2 | 3 | 8 | 5
3 | 5 | 20 | 15
4 | 14 | 20 | 6
5 | 20 | 20 | 0
6 | 17 | 23 | 6
7 | 15 | 20 | 5
8 | 20 | 28 | 8
9 | 20 | 20 | 0
10 | 20 | 24 | 4
11 | 30 | 30 | 0
  TSij = tj(L) – ti(E) – yij = tj(L) – EFTij = LFTij - EFTij
  FSij = tj(E) – ti(E) – yij = tj(E) – EFTij
  SSij = tj(L) – ti(L) – yij = LSTij – ti(L)
  ISij = tj(E) – ti(L) – yij

## Slide 8: Exercise 2
Time
5
15
10
4
14
9
3
13
8
2
12
7
1
11
6

## Slide 9: ILP model
Minimize Z
ST:
x21 + x22 + x23 + x24 = 1
x31 + x32 + x33 = 1
x41 + x42 + x43 + x44 + x45 + x46 + x47 = 1
x56 + x57 + x58 = 1
x63 + x64 + x65 + x66 + x67 + x68 + x69 = 1
x7,10 + x7,11 + x7,12 = 1
x85 + x86 + x87 + x88 + x89 + x8,10 + x8,11 + x8,12 + x8,13 + x8,14 = 1
x98 + x99 + x9,10 + x9,11 + x9,12 + x9,13 + x9,14 = 1

## Slide 10: ILP model
1 x21 + 2 x22 + 3 x23 + 4 x24 + 4 <= 6 x56 + 7 x57 + 8 x58
1 x21 + 2 x22 + 3 x23 + 4 x24 + 4 <= 5 x85 + 6 x86 + 7 x87 + 8 x88 + 9 x89 + 10 x8,10 + 11 x8,11 + 12 x8,12 + 13 x8,13 + 14 x8,14
1 x31 + 2 x32 + 3 x33 + 5 <= 6 x56 + 7 x57 + 8 x58
1 x41 + 2 x42 + 3 x43 + 4 x44 + 5 x45 + 6 x46 + 7 x47 + 2 <= 3 x63 + 4 x64 + 5 x65 + 6 x66 + 7 x67 + 8 x68 + 9 x69
6 x56 + 7 x57 + 8 x58 + 4 <= 10 x7,10 + 11 x7,11 + 12x7,12
3 x63 + 4 x64 + 5 x65 + 6 x66 + 7 x67 + 8 x68 + 9 x69 + 5 <= 8 x98 + 9 x99 + 10 x9,10 + 11 x9,11 + 12 x9,12 + 13 x9,13 + 14 x9,14

## Slide 11: ILP model
5 x21 + 3 x31 + 4 x41 <= 10
5 (x21 + x22) + 3 (x31 + x32) + 4 (x41 + x42) <= 10
5 (x21 + x22 + x23) + 3 (x31 + x32 + x33) + 4 (x42 + x43) + 3 x63 <= 10
5 (x21 + x22 + x23 + x24) + 3 (x31 + x32 + x33) + 4 (x43 + x44) + 3 (x63 + x64) <= 10
5 (x22 + x23 + x24) + 3 (x31 + x32 + x33) + 4 (x44 + x45) + 3 (x63 + x64 + x65) + 3 x85 <= 10
5 (x23 + x24) + 3 (x32 + x33) + 4 (x45 + x46) + 4 x56 + 3 (x63 + x64 + x65 + x66) + 3 (x85 + x86) <= 10
5 x24 + 3 x33 + 4 (x46 + x47) + 4 (x56 + x57) + 3 (x63 + x64 + x65 + x66 + x67) + 3 (x86 + x87) <= 10
4 x47 + 4 (x56 + x57 + x58) + 3 (x64 + x65 + x66 + x67 + x68) + 3 (x87 + x88) + 6 x98 <= 10
4 (x56 + x57 + x58) + 3 (x65 + x66 + x67 + x68 + x69) + 3 (x88 + x89) + 6 (x98 + x99) <= 10
4 (x57 + x58) + 3 (x66 + x67 + x68 + x69) + 5 x7,10 + 3 (x89 + x8,10) + 6 (x99 + x9,10) <= 10
4 x58 + 3 (x67 + x68 + x69) + 5 (x7,10 + x7,11) + 3 (x8,10 + x8,11) + 6 (x9,10 + x9,11) <= 10
3 (x68 + x69) + 5 (x7,10 + x7,11 + x7,12) + 3 (x8,11 + x8,12) + 6 (x9,11 + x9,12) <= 10
3 x69 + 5 (x7,10 + x7,11 + x7,12) + 3 (x8,12 + x8,13) + 6 (x9,12 + x9,13) <= 10
5 (x7,11 + x7,12) + 3 (x8,13 + x8,14) + 6 (x9,13 + x9,14) <= 10
5 x7,12 + 3 x8,14 + 6 x9,14 <= 10
10 x7,10 + 11 x7,11 + 12x7,12 + 4 <= Z
5 x85 + 6 x86 + 7 x87 + 8 x88 + 9 x89 + 10 x8,10 + 11 x8,11 + 12 x8,12 + 13 x8,13 + 14 x8,14 + 2 <= Z
8 x98 + 9 x99 + 10 x9,10 + 11 x9,11 + 12 x9,12 + 13 x9,13 + 14 x9,14 + 2 <= Z

## Slide 12: Exercise 3
Critical path calculations easily indicate that path 1-2-5-8-9 is the longest path with a length of 0 + 1 + 3 + 2 + 0 = 6
Act. 3: can be scheduled in parallel with act. 5 for 2 periods  6 + 2 – 2 = 6
Act. 4: can be scheduled in parallel with act. 8 for 1 period  6 + 3 – 1 = 8
Act. 6: can be scheduled in parallel with act. 5 for 2 periods  6 + 3 – 2 = 7
Act. 7: cannot be scheduled in parallel with act. 5  6 + 1 – 0 = 7
The critical sequence lower bound is therefore max (6,8,7,7) = 8
Time
5
4
3
2
1
6
2 (1/2)
5 (2/1)
8 (1/3)
4 (2/0)
6 (1/1)
3 (1/2)
7 (2/1)

## Slide 13: Exercise 4
LB = 13
2 <. 4
LB = 13
4 <. 2
LB = 14
4 <. 3
LB = 15
4 <. 8
LB = 13
8 <. 4
LB = 15
4 <. 5
LB = 16
7 <. 9
LB = 15
9 <. 7
LB = 17
3 <. 6
LB = 14
3 <. 2
LB = 17
2 <. 3
LB = 19

## Slide 14: Exercise 4
Step 1: T = 9999; p = m = 0; critical path lb = 13 (path 3-5-7); critical sequence lb = 13; PS = S = {1}; t1 = 0; C = {2,3,4}
Step 2: m = 0; S = {}; cutset not dominated; E = {2,3,4}
Step 3: theorems 3 and 4 are not applicable
Step 4: PS = {1,2,3,4}; S = {2,3,4}; t2 = 4; t3 = 5; t4 = 2; C = {5,6,8}; 5 + 3 + 4 = 12 > 10  resource conflict
Step 5: p = 1; D(1) = {{2},{3},{4}}
  D1 = {2}, G1 ={(4,2)}, L1 = 14
  D2 = {3}, G2 ={(4,3)}, L2 = 15
  D3 = {4}, G3 ={(2,4)}, L3 = 13 (critical sequence lb = 15)
  Select D3; D(1) = {{2},{3}}

## Slide 15: Exercise 4
Step 6: DS={}; H = H + {(2,4)}; t4 = 9999; PS = {1,2,3}; S = {2,3}; C = {4,5,8}
Step 2: m = 4; S = {3}; C = {4,5,8}; cutset not dominated; E = {4,8};
Step 4: PS = {1,2,3,4,8}; S = {3,4,8}; t4 = 6; t8 = 6; C = {5,6}; 3 + 4 + 3 = 10  no resource conflict
Step 2: m = 5; S = {4,8}; C = {5,6}; cutset not dominated; E = {5};
Step 4: PS = {1,2,3,4,5,8}; S = {4,5,8}; t5 = 9; C = {6,7}; 4 + 4 + 3 = 11 > 10  resource conflict
Step 5: p = 2; D(2) = {{4},{5},{8}}
  D1 = {4}, G1 ={(8,4)}, L1 = 15
  D2 = {5}, G2 ={(4,5)}, L2 = 16 (critical sequence lb!)
  D3 = {8}, G3 ={(4,8)}, L3 = 13
  Select D3; D(2) = {{4},{5}}

## Slide 16: Exercise 4
Step 6: DS={}; H = H + {(4,8)}; t8 = 9999; PS = {1,2,3,4,5}; S = {4,5}; C = {6,7,8}
Step 2: m = 6; S = {5}; C = {6,7,8}; cutset not dominated; E = {6,8};
Step 4: PS = {1,2,3,4,5,6,8}; S = {5,6,8}; t6 = 11; t8 = 8; C = {7,9}; 4 + 3 + 3 = 10  no resource conflict
Step 2: m = 8; S = {5,6}; C = {7,9}; cutset not dominated; E = {};
Step 2: m = 9; S = {6}; C = {7,9}; cutset not dominated; E = {7};
Step 4: PS = {1,2,3,4,5,6,7,8}; S = {6,7}; t7 = 13; C = {9}; 3 + 5 = 8  no resource conflict
Step 2: m = 11; S = {7}; C = {9}; cutset not dominated; E = {9};
Step 4: PS = {1,2,3,4,5,6,7,8,9}; S = {7,9}; t9 = 13; C = {10}; 5 + 6 = 11 > 10  resource conflict
Step 5: p = 3; D(3) = {{7},{9}}
  D1 = {7}, G1 ={(9,7)}, L1 = 17
  D2 = {9}, G2 ={(7,9)}, L2 = 15
  Select D2; D(3) = {{7}}

## Slide 17: Exercise 4
Step 6: DS={}; H = H + {(7,9)}; t9 = 9999; PS = {1,2,3,4,5,6,7,8}; S = {7}; C = {9}
Step 2: m = 13; S = {}; C = {9}; cutset not dominated; E = {9};
Step 3: Act. 9 can only be scheduled by itself: PS = {1,2,3,4,5,6,7,8,9}; S = {9}; t9 = 15; C = {10};
Step 2: m = 15; S = {}; C = {10}; cutset not dominated; E = {10};
Step 3: Act. 10 can only be scheduled by itself: PS = {1,2,3,4,5,6,7,8,9,10}; S = {10}; t10 = 15; The dummy end activity is finished, thus the schedule is complete with a length of 15.
Step 7: Remove the extra delaying constraints (7,9): the delaying alternative {7} needn’t be considered as the lower bound is larger than or equal to 15.
Step 7: Remove the extra delaying constraints (4,8): the other delaying alternatives at this level needn’t be considered as the lower bounds are larger than or equal to 15.
Step 7: Remove the extra delaying constraints (2,4): select delaying alternative {2} as it has a lower bound of 14.

## Slide 18: Exercise 4
Step 6: DS={}; H = H + {(4,2)}; t2 = 9999; PS = {1,3,4}; S = {3,4}; C = {2,6}
Step 2: m = 2; S = {3}; C = {2,6}; cutset not dominated; E = {2,6};
Step 4: PS = {1,2,3,4,6}; S = {2,3,6}; t2 = 6; t6 = 7; C = {5,8,9}; 5 + 3 + 3 = 11 > 10  resource conflict
Step 5: p = 2; D(1) = {{2},{3},{6}}
  D1 = {2}, G1 ={(3,2)}, L1 = 17
  D2 = {3}, G2 ={(2,3)}, L2 = 19
  D3 = {6}, G3 ={(3,6)}, L3 = 14
  Select D3; D(2) = {{2},{3}}
Step 6: DS={}; H = H + {(3,6)}; t6 = 9999; PS = {1,2,3,4}; S = {2,3}; C = {5,6,8}
Step 2: m = 5; S = {2}; C = {5,6,8}; cutset not dominated; E = {6};
Step 4: PS = {1,2,3,4,6}; S = {2,6}; t6 = 10; C = {5,8,9}; 5 + 3 = 8  no resource conflict
Step 2: m = 6; S = {6}; C = {5,8,9}; cutset not dominated; E = {5,8};

## Slide 19: Exercise 4
Step 4: PS = {1,2,3,4,5,6,8}; S = {5,6,8}; t5 = 10; t8 = 8; C = {5,8,9}; 4 + 3 + 3 = 10  no resource conflict
Step 2: m = 8; S = {5,6}; C = {7,9}; cutset not dominated; E = {};
Step 2: m = 10; S = {}; C = {7,9}; cutset not dominated; E = {7,9};
Step 3: Act. 7 can only be scheduled by itself: PS = {1,2,3,4,5,6,7,8}; S = {7}; t7 = 14;
Step 2: m = 14; S = {}; C = {9}; cutset not dominated; E = {9};
Step 3: Act. 9 can only be scheduled by itself: PS = {1,2,3,4,5,6,7,8,9}; S = {9}; t7 = 16; This is beyond the upper bound of 15, so backtrack.
Step 7: Remove the extra delaying constraints (3,6): the other delaying alternatives at this level needn’t be considered as the lower bounds are larger than or equal to 15.
Step 7: Remove the extra delaying constraints (4,2): the other delaying alternatives at this level needn’t be considered as the lower bounds are larger than or equal to 15.