## Slide 1: Solutions Homework 2

## Slide 2: Question 1: first planning cycle
Early start solution with sum of squares = 1153
List activities in increasing order of their total float (smallest activity as tie-breaker): (1,3,7,6,10,2,5,9,12,4,8,11,13)
Activity 11: TF = 0
Activity 8: 1/1153, 2/1103, 3/1103, 4/1143, 5/1163, 6/1183, 7/1163  select 3/1103
Activity 4: 0/1103, 1/1103, 2/1073  select 2/1073
Activity 12: 11/1073, 12/1073  select 12/1073
Activity 9: 6/1073, 7/1089, 8/1089, 9/1089, 10/1073, 11/1057  select11/1057
Activity 5: 2/1057, 3/1057, 4/1049, 5/1041, 6/1033, 7/1009  select 7/1009
Activity 2: 0/1009, 1/1015, 2/1033, 3/1045, 4/1045, 5/1015  keep unchanged
Activity 10: 7/1009, 8/1017  keep unchanged
Activity 6: Can’t be moved
Activities 7 and 3: TF = 0
End of first planning cycle

## Slide 3: Question 1: second planning cycle
Same activity list: (1,3,7,6,10,2,5,9,12,4,8,11,13)
Activity 11: TF = 0
Activity 8: 3/1009, 4/1009, 5/1029, 6/1049, 7/1069  select 4/1009
Activity 4: 0/1039, 1/1039, 2/1009, 3/1009  select 3/1009
Activity 12: 12/1009  keep unchanged
Activity 9: 11/1009  keep unchanged
Activity 5: 2/1057, 3/1057, 4/1049, 5/1041, 6/1033, 7/1009  keep unchanged
Activity 2: 0/1009, 1/997, 2/1003, 3/1033, 4/1045, 5/1045  select 1/997
Activity 10: 7/997, 8/1005  keep unchanged
Activity 6: 2/997 keep unchanged
Activities 7 and 3: TF = 0
End of second planning cycle

## Slide 4: Question 1: third planning cycle
Same activity list: (1,3,7,6,10,2,5,9,12,4,8,11,13)
Activity 11: can’t move
Activity 8: 4/997, 5/1017, 6/1037, 7/1057 keep unchanged
Activity 4: 0/1009, 1/1027, 2/1015 , 3/997  keep unchanged
Activity 12: 12/997  keep unchanged
Activity 9: 11/997  keep unchanged
Activity 5: 3/1045, 4/1037, 5/1029, 6/1021, 7/997  keep unchanged
Activity 2: 0/1009, 1/997, 2/1003, 3/1033, 4/1045, 5/1045  keep unchanged
Activity 10: 7/997, 8/1005  keep unchanged
Activity 6: 2/997 keep unchanged
Activities 7 and 3: TF = 0
End of third and last planning cycle
The best leveled usage found has a value of 997

## Slide 5: Question 2: minimal resource availability
Maximal resource requirements: 5/6/6
5/-/-: no
6/-/-: no
7/-/-: yes
  -/6/-: no
  -/7/-: no
  -/8/-: yes
    -/-/6: no
    -/-/7: yes

## Slide 6: Question 2: partial efficient points
7/8/-: no
7/9/-: yes
  8/8/-: yes
PES2:
  7/9
  8/8
7/-/7: no
7/-/8: yes
  8/-/7: no
  9/-/7: no
  10/-/7: yes
PES3:
  7/8
  10/7
EP = {7,8,10}

## Slide 7: Question 2: efficient points
7/9/8 (71)
8/8/8 (72)
10/8/7 (78)
These are already in sorted order
7/9/8 (71): no
Add 7/10/8 (74) and 7/9/9 (73) (remark: 8/9/8 (75) is dominated by 8/8/8 (72))
8/8/8 (72): no
Add 9/8/8 (76), 8/9/8 (75) and 8/8/9 (74)
7/9/9 (73): yes (optimal solution, even with a project length of 41)

## Slide 8: Question 3: Early tree
3
4
2
5
1
6
7
0/0
0
3/3
-100
1/2
200
4/1
200
2/2
-100
2/1
50
0/0
0
0
3
1
5
3
5
8
NPV = 241.73

## Slide 9: Question 3: Current tree
3
4
2
5
1
6
7
0/0
0
3/3
-100
1/2
200
4/1
200
2/2
-100
2/1
50
0/0
0
0
8
1
5
3
5
8
NPV = 246.46

## Slide 10: Question 3: recursion
Recursion(1) SA={1}, CA={1} and DC = 0.00
  Recursion(3) SA={3}, CA={1,3} and DC = 198.01
    Recursion(4) SA={4}, CA={1,3,4} and DC = 190.25
  SA’={3,4} and DC’ = 388.26 >= 0
    Recursion(5) SA={5}, CA={1,3,4,5} and DC = -97.04
      Recursion(6) SA={6}, CA={1,3,4,5,6} and DC = 47.56
    SA’={5,6} and DC’ = -49.48 < 0  delay {5,6}: remove (3,5) and add (6,7)

## Slide 11: Question 3: Updated tree
3
4
2
5
1
6
7
0/0
0
3/3
-100
1/2
200
4/1
200
2/2
-100
2/1
50
0/0
0
0
8
1
5
6
8
8
NPV = 247.92

## Slide 12: Question 3: recursion
Recursion(1) SA={1}, CA={1} and DC = 0.00
  Recursion(3) SA={3}, CA={1,3} and DC = 198.01
    Recursion(4) SA={4}, CA={1,3,4} and DC = 190.25
  SA’={3,4} and DC’ = 388.26 >= 0
  SA’={1,3,4} and DC’ = 388.26

## Slide 13: Question 3: recursion
  Recursion(7) SA={7}, CA={1,3,4,7} and DC = 0
    Recursion(2) SA={2}, CA={1,2,3,4,7} and DC = -92.31
  SA’={2,7} and DC’ = -92.31 < 0
    Recursion(6) SA={6}, CA={1,2,3,4,6,7} and DC = 46.16
      Recursion(5) SA={5}, CA={1,2,3,4,5,6,7} and DC = -94.18
    SA’={5,6} and DC’ = -48.02 < 0
  SA’={2,5,6,7} and DC’ = -140.33 < 0
SA’={1,2,3,4,5,6,7} and DC’ = 247.92

## Slide 14: Question 3: resource profile
Workers
Time
2
6
5
3
4
Resource conflict: activities 2 and 5
 2 before 5 or 5 before 2

## Slide 15: Question 3: 2 before 5
3
4
2
5
1
6
7
0/0
0
3/3
-100
1/2
200
4/1
200
2/2
-100
2/1
50
0/0
0
0
4
1
5
6
8
8
NPV = 244.16

## Slide 16: Question 3: 5 before 2
3
4
2
5
1
6
7
0/0
0
3/3
-100
1/2
200
4/1
200
2/2
-100
2/1
50
0/0
0
0
8
1
5
5
7
8
NPV = 247.44

## Slide 17: Question 3: branch-and-bound tree
Root
NPV = 247.92
5 before 2
NPV = 247.44
2 before 5
NPV = 244.16

## Slide 18: Question 4
1|0
2|2
3|5
4|7
2
1
( )-(0,2)
4
1
( )-(0,6)
3
1
( )-(0,1)
4
2
( )-(0,2)
2
1
( )-(0,6)
Non-breakthrough
Breakthrough
q4 = 1
(2,1)
(1,2)
(1,3)
(∞,0)

## Slide 19: Question 4
1|0
2|2
3|5
4|7
2
1
( )-(1,1)
4
1
( )-(0,6)
3
1
( )-(1,0)
4
2
( )-(0,2)
2
1
( )-(1,5)
(1,1)
Non-breakthrough
(∞,0)

## Slide 20: Question 4
1|0
2|2
3|4
4|6
2
1
( )-(1,1)
4
1
( )-(0,6)
3
1
( )-(1,0)
4
2
( )-(0,2)
2
1
( )-(1,5)
(1,1)
(1,2)
Breakthrough
q4 = 1
(∞,0)

## Slide 21: Question 4
1|0
2|2
3|4
4|6
2
1
( )-(2,0)
4
1
( )-(0,6)
3
1
( )-(1,0)
4
2
( )-(1,1)
2
1
( )-(1,5)
Breakthrough
q4 = 5
(6,1)
(5,3)
(∞,0)

## Slide 22: Question 4
1|0
2|2
3|4
4|6
2
1
( )-(2,0)
4
1
( )-(5,1)
3
1
( )-(1,0)
4
2
( )-(1,1)
2
1
( )-(6,0)
(1,1)
Non-breakthrough
(∞,0)

## Slide 23: Question 4
1|0
2|2
3|4
4|6
2
1
( )-(2,0)
4
1
( )-(5,1)
3
1
( )-(1,0)
4
2
( )-(1,1)
2
1
( )-(6,0)
(1,1)
(∞,0)

## Slide 24: Question 4
1|0
2|1
3|4
4|5
2
1
( )-(2,0)
4
1
( )-(5,1)
3
1
( )-(1,0)
4
2
( )-(1,1)
2
1
( )-(6,0)
(∞,0)
A project length of 5 is obtained
after crashing activities (1,2) and
(3,4).
Remark that activity (2,3) was first
shortened and then lengthened.
Remark: total cost of reducing the
project length from 7 to 5 is 8 (2
for reducing the length of act. (1,2)
and 6 for reducing the length of
act. (3,4)).